## ProductBackLog
Project Name:StorySphere: A Safe and Interactive Digital Platform for Writers and Readers Group Members: Efe Şahin, Selcen Aksu, Azra Bayhan, Berkay Gökçe, İsmet Eren Çetin, Ayça Baygar, Zeynep Ekin Zengin
# | Product BackLog
1 | User Registration & Email Verification
2 | User Login & Session Management
3 | Age Verification (e-Devlet)
4 | Database Design & Backend APIs
5 | Security Mechanisms
6 | Author Profile Management
7 | Author Post & Book Link Sharing
8 | Story Creation
9 | Story Editing & Deletion
10 | Responsive User Interface
11 | Comments, Ratings & Reviews
12 | Real-time Chat
13 | Book Clubs / Reading Groups
14 | Search & Advanced Filtering
15 | Bookmarking & Text Highlighting
16 | Notification System
17 | Collaborative Writing
18 | Shared Reading Sessions
19 | Live Streaming
20 | Multi-format Content Support
21 | AI Translation & AI Writing assistant
22 | Automated Content Moderation
23 | Multi-format Content Support
24 | Admin Moderation Dashboard
25 | Testing & Debugging

## Sprint-1
SPRINT-1
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer, Product Owner | User Registration & Email Verification | In Progress | High | 02.02.2026 | 04.02.2026 | 3 | to register and verify email so that securely access the platform
Developer | User Login & Session Management | Ready to Start | High | 05.02.2026 | 09.02.2026 | 3 | secure login and session management so that account stays protected
Developer | Age Verification (e-Devlet) | Ready to Start | High | 05.02.2026 | 05.02.2026 | 1 | age verification so that age-restricted content is properly controlled
Developer | Database Design & Backend APIs | Ready to Start | High | 06.02.2026 | 11.02.2026 | 4 | a structured database and backend APIs so that platform features work reliably
8
BACKLOG
As a user, I want to register and verify my email so that I can securely access the platform
STATUS: Ready to Start
As a user, I want secure login and session management so that my account stays protected
STATUS: Ready to Start
P.O
Dev
As a user, I want age verification so that age-restricted content is properly controlled
STATUS: Ready to Start
Dev

## Sprint-2
SPRINT-2
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Responsive User Interface | Not Started | High | 2026-02-11 | 2026-02-16 | 4 | to edit and delete stories so that user manage content easily
Developer | Author Profile Management | Not Started | High | 2026-02-17 | 2026-02-19 | 3 | encryption and secure authentication so that user data is protected
Developer | Author Post & Book Link Sharing | Not Started | Medium | 2026-02-20 | 2026-02-24 | 3 | to create and edit profile so that present to readers
Developer | Story Creation | Not Started | High | 2026-02-17 | 2026-02-19 | 3 | to share posts and external book links so that promote work
Developer | Story Editing & Deletion | Not Started | High | 2026-02-20 | 2026-02-24 | 3 | to publish stories so that readers access content
10
BACKLOG
As a writer, to share posts and external book links so that promote work
STATUS: Not Started
As a writer, to create and edit profile so that present to readers
STATUS: Not Started
Dev
Dev
As a writer to publish stories so that readers can access content
STATUS: Not Started
As a writer, to edit and delete stories so that manage content easily
STATUS: Not Started
dev
dev

## Sprint-3
SPRINT-3
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Comments, Ratings & Reviews | Not Started | High | 2026-02-24 | 2026-02-26 | 3 | to comment on, rate, and review stories so that share feedback
Developer | Real-time Chat | Not Started | Medium | 2026-02-24 | 2026-02-27 | 4 | instant messaging so that communicate with others in real time
Developer | Book Clubs / Reading Groups | Not Started | Low | 2026-02-24 | 2026-02-25 | 2 | to join reading groups so that discuss books with others
Developer | Search & Advanced Filtering | Not Started | High | 2026-02-25 | 02.03.2026 | 4 | to search and filter stories so that quickly find relevant content
Developer | Bookmarking & Text Highlighting | Not Started | Medium | 02.03.2026 | 04.03.2026 | 3 | to bookmark and highlight text so that save important parts while reading
Developer | Notification System | Not Started | Medium | 04.03.2026 | 06.03.2026 | 3 | to receive notifications so that stay updated about platform activity
Developer | Admin Moderation Dashboard | Not Started | Medium | 06.03.2026 | 2026-03-10 | 3 | to manage users and content so that maintain platform quality
11
BACKLOG
As a user, to comment on, rate, and review stories so that share feedback
STATUS: Not Started
As a user, to bookmark and highlight text so that save important parts while reading
STATUS: Not Started
Dev
Dev
As a user, to receive notifications so that stay updated about platform activity
STATUS: Not Started
As a user, to search and filter stories so that quickly find relevant content
STATUS: Not Started
As a user, to join reading groups so that discuss books with others
STATUS: Not Started
As a user, instant messaging so that communicate with others in real time
STATUS: Not Started
Dev
Dev
Dev
Dev

## Sprint-4
SPRINT-4
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | AI Translation & AI Writing Assistant | Not Started | Medium | 2026-03-10 | 2026-03-12 | 3 | automatic story translation so that read stories in preferred language, AI writing suggestions so that improve writing process
Developer | Shared Reading Sessions | Not Started | Low | 2026-03-11 | 2026-03-12 | 2 | to join shared reading sessions so that read together with others
Developer | Live Streaming | Not Started | Low | 2026-03-12 | 2026-03-13 | 2 | live sessions with authors so that interact with them directly
Developer | Multi-format Content Support | Not Started | Medium | 2026-03-13 | 2026-03-17 | 3 | text, manga, and audiobook formats so that consume content in different ways
Developer | Collaborative Writing | Not Started | Medium | 2026-03-13 | 2026-03-17 | 3 | to co-write stories with others so that create content together
Developer | Automated Content Moderation | Not Started | High | 2026-03-13 | 2026-03-18 | 4 | inappropriate content to be detected automatically so that the platform remains safe
Developer | Security Mechanisms | Not Started | High | 2026-03-18 | 2026-03-23 | 4 | to test and debug the system so that the platform is stable and reliable
Developer | Testing & Debugging | Not Started | High | 2026-03-23 | 2026-03-30 | 6 | encryption and secure authentication so that user data is protected
15
BACKLOG
As a writer, to co-write stories with others so that create content together
STATUS: Not Started
As a user, to join shared reading sessions so that read together with others
STATUS: Not Started
Dev
Dev
As a user, text, manga, and audiobook formats so that consume content in different ways
STATUS: Not Started
Dev
As a user, automatic story translation so that read stories in preferred language As a writer, AI writing suggestions so that improve writing process
STATUS: Not Started
As a user, live sessions with authors so that interact with them directly
STATUS: Not Started
Dev
Dev
As a developer,to test and debug the system so that the platform is stable and reliable.
STATUS: Not Started
Dev

## KeyDropdowns
KEY DROPDOWNS - DO NOT DELETE
PRIORITY KEY | STATUS KEY
High | In Progress
Medium | Ready to Start
Low | Complete
On Hold
Testing
Not Started

## Templates
TEMPLATES
ASSIGNED TO | KANBAN CARDS
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here