## ProductBackLog
Project Name:StorySphere: A Safe and Interactive Digital Platform for Writers and Readers Group Members: Efe Şahin, Selcen Aksu, Azra Bayhan, Berkay Gökçe, İsmet Eren Çetin, Ayça Baygar, Zeynep Ekin Zengin
# | Product BackLog
1 | User Registration & Email Verification
2 | User Login & Session Management
3 | Age Verification (e-Devlet)
4 | Database Design & Backend APIs
5 | Security Mechanisms
6 | Author Profile Management
7 | Author Post & Book Link Sharing
8 | Story Creation
9 | Story Editing & Deletion
10 | Responsive User Interface
11 | Comments, Ratings & Reviews
12 | Real-time Chat
13 | Book Clubs / Reading Groups
14 | Search & Advanced Filtering
15 | Bookmarking & Text Highlighting
16 | Notification System
17 | Collaborative Writing
18 | Shared Reading Sessions
19 | Live Streaming
20 | Multi-format Content Support
21 | AI Translation
20 | AI Writing Assistant
20 | Automated Content Moderation
20 | Admin Moderation Dashboard
20 | Testing & Debugging

## Sprint-1
SPRINT-1
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer, Product Owner | User Registration & Email Verification | In Progress | High | 2026-02-01 | 2026-02-07 | 6 | to register and verify my email so that I can securely access the platform
Developer | User Login & Session Management | Ready to Start | High | 2026-02-07 | 2026-02-12 | 5 | secure login and session management so that my account stays protected
Developer | Age Verification (e-Devlet) | Ready to Start | High | 2026-02-12 | 2026-02-18 | 6 | age verification so that age-restricted content is properly controlled
Developer | Database Design & Backend APIs | Ready to Start | High | 2026-02-18 | 2026-02-23 | 5 | a structured database and backend APIs so that platform features work reliably
Developer | Security Mechanisms | Ready to Start | High | 2026-02-23 | 2026-02-28 | 5 | encryption and secure authentication so that user data is protected
27
BACKLOG
As a user, I want to register and verify my email so that I can securely access the platform
STATUS: Ready to Start
As a user, I want secure login and session management so that my account stays protected
STATUS: Ready to Start
P.O
Dev
As a user, I want age verification so that age-restricted content is properly controlled
STATUS: Ready to Start
Dev
As a system, I want a structured database and backend APIs so that platform features work reliably
STATUS: Ready to start
Dev
As a system, I want encryption and secure authentication so that user data is protected
STATUS: Ready to Start
Dev

## Sprint-2
SPRINT-2
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Author Profile Management | Not Started | High | 2026-02-28 | 2026-03-04 | 6 | encryption and secure authentication so that user data is protected
Developer | Author Post & Book Link Sharing | Not Started | Medium | 2026-03-04 | 2026-03-09 | 5 | to create and edit my profile so that I can present myself to readers
Developer | Story Creation | Not Started | High | 2026-03-09 | 2026-03-15 | 6 | to share posts and external book links so that I can promote my work
Developer | Story Editing & Deletion | Not Started | High | 2026-03-15 | 2026-03-21 | 6 | to publish stories so that readers can access my content
Developer | Responsive User Interface | Not Started | High | 2026-03-21 | 2026-03-28 | 7 | to edit and delete my stories so that I can manage my content easily
30
BACKLOG
As a system, I want encryption and secure authentication so that user data is protected.
STATUS: Not Started
As a writer, I want to share posts and external book links so that I can promote my work
STATUS: Not Started
Dev
As a writer, I want to create and edit my profile so that I can present myself to readers
STATUS: Not Started
Dev
Dev
As a writer, I want to publish stories so that readers can access my content
STATUS: Not Started
As a writer, I want to edit and delete my stories so that I can manage my content easily
STATUS: Not Started
dev
dev

## Sprint-3
SPRINT-3
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Comments, Ratings & Reviews | Not Started | High | 2026-03-28 | 2026-04-03 | 6 | to comment on, rate, and review stories so that I can share feedback
Developer | Real-time Chat | Not Started | Medium | 2026-04-03 | 2026-04-08 | 5 | instant messaging so that I can communicate with others in real time
Developer | Book Clubs / Reading Groups | Not Started | Low | 2026-04-08 | 2026-04-12 | 4 | to join reading groups so that I can discuss books with others
Developer | Search & Advanced Filtering | Not Started | High | 2026-04-12 | 2026-04-16 | 4 | to search and filter stories so that I can quickly find relevant content
Developer | Bookmarking & Text Highlighting | Not Started | Medium | 2026-04-16 | 2026-04-22 | 6 | to bookmark and highlight text so that I can save important parts while reading
Developer | Notification System | Not Started | Medium | 2026-04-22 | 2026-04-27 | 5 | to receive notifications so that I can stay updated about platform activity
30
BACKLOG
As a reader, I want to comment on, rate, and review stories so that I can share feedback
STATUS: Not Started
As a user, I want to bookmark and highlight text so that I can save important parts while reading
STATUS: Not Started
Dev
Dev
As a user, I want to receive notifications so that I can stay updated about platform activity
STATUS: Not Started
As a user, I want to search and filter stories so that I can quickly find relevant content
STATUS: Not Started
As a user, I want to join reading groups so that I can discuss books with others
STATUS: Not Started
As a user, I want instant messaging so that I can communicate with others in real time
STATUS: Not Started
Dev
Dev
Dev
Dev

## Sprint-4
SPRINT-4
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Collaborative Writing | Not Started | Medium | 2026-04-27 | 2026-05-01 | 4 | to co-write stories with others so that we can create content together
Developer | Shared Reading Sessions | Not Started | Low | 2026-05-01 | 2026-05-04 | 3 | to join shared reading sessions so that I can read together with others
Developer | Live Streaming | Not Started | Low | 2026-05-04 | 2026-05-07 | 3 | live sessions with authors so that I can interact with them directly
Developer | Multi-format Content Support | Not Started | Medium | 2026-05-07 | 2026-05-11 | 4 | text, manga, and audiobook formats so that I can consume content in different ways
Developer | AI Translation | Not Started | Medium | 2026-05-11 | 2026-05-15 | 4 | automatic story translation so that I can read stories in my preferred language
Developer | AI Writing Assistant | Not Started | Low | 2026-05-15 | 2026-05-18 | 3 | AI writing suggestions so that I can improve my writing process
Developer | Automated Content Moderation | Not Started | High | 2026-05-18 | 2026-05-26 | 5 | inappropriate content to be detected automatically so that the platform remains safe
Developer | Admin Moderation Dashboard | Not Started | Medium | 2026-05-26 | 2026-05-30 | 4 | to manage users and content so that I can maintain platform quality
Developer | Testing & Debugging | Not Started | High | 2026-05-30 | 2026-06-04 | 5 | to test and debug the system so that the platform is stable and reliable
35
BACKLOG
As a writer, I want to co-write stories with others so that we can create content together
STATUS: Not Started
As a user, I want to join shared reading sessions so that I can read together with others
STATUS: Not Started
Dev
Dev
As a user, I want text, manga, and audiobook formats so that I can consume content in different ways
STATUS: Not Started
Dev
As a user, I want automatic story translation so that I can read stories in my preferred language
STATUS: Not Started
As an admin, I want to manage users and content so that I can maintain platform quality
STATUS: Not Started
As a user, I want live sessions with authors so that I can interact with them directly
STATUS: Not Started
As a writer, I want AI writing suggestions so that I can improve my writing process
STATUS: Not Started
As a platform, I want inappropriate content to be detected automatically so that the platform remains safe
STATUS: Not Started
Dev
Dev
Dev
Dev
Dev
As a developer, I want to test and debug the system so that the platform is stable and reliable.
STATUS: Not Started
Dev

## KeyDropdowns
KEY DROPDOWNS - DO NOT DELETE
PRIORITY KEY | STATUS KEY
High | In Progress
Medium | Ready to Start
Low | Complete
On Hold
Testing
Not Started

## Templates
TEMPLATES
ASSIGNED TO | KANBAN CARDS
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here